## Sheet1
As a/an… | I want to… | So that… | Developer | Time Estimate | Dev Time | Tester(s) | Time Estimate | Dev Time
Director of Research | search for an author | I can get the information about what I want | Lynne Tian Yuan | 1 hrs | 0.5 hrs
Director of Research | change the views | views classified by first author, last author, sole author | Tian Yuan Lynne | 2 hrs | 1 hrs
Director of Research | write new function for publications details | I can get the information about publications details | Tian Yuan Lynne | 4 hrs | 3 hrs | Lynne Tian Yuan | 2 hrs | 1 hrs
Director of Research | implementation for sorting algorithm | using the last name as the secondary sort criterion | Mark kynigos Mariam | 2.5 hrs | 3 hrs | Lynne Tian Yuan | 1 hrs | 0.5 hrs