## User stories
As a/an…	I want to…	So that…	Developer	Time Estimate	Dev Time	Tester(s)	Testing time estimate	Testing Time
Researcher who hasn't used the application before	see an explanation of the functionality	I can get the information I want.
Research support manager	get a monthly update on publication activity	I can put new publications in the school newsletter.
Academic	have a UI that looks nice on a phone/tablet	I can use the app when I'm travelling.
Director of Research	sort the information	I can see which authors have the most publications.	lynne	2.5 hrs	1 hrs	YingYing Huang, Myriam Awaji	2 hrs	N/A
Director of Research	sort the information	I can see which authors have the most co-authors.	lynne	2.5 hrs	1 hrs	YingYing Huang, Myriam Awaji	2 hrs	N/A
Director of Research	sort the tables by author name	I can get statistics for individual members of staff.	lynne, Mark Kynigos	5 hrs	7 hrs	Mark Kynigos	2 hrs	N/A
Director of Research	convert a given data table to a graph	I can look for trends in the data.
Director of Research	see how many times a person appears first in the author list	I see how much 'hands-on' research s/he has done.	lynne	2.5 hrs	3 hrs	YingYing Huang, Myriam Awaji	2 hrs	2 hrs
Director of Research	see how many times a person appears last in the author list	I can see how many research projects s/he has managed.	lynne	2.5 hrs	3 hrs	YingYing Huang, Myriam Awaji	2 hrs	2 hrs
Research Support Manager	merge different versions of an author's name	author statistics are represented more accurately.
Director of Research	know which authors are from the School	I can promote the research of our academics.
Director of Research	know the degrees of separation between two individuals	I can better understand the research network.
Director of Research	visualise the research network of a given author	I can better understand the research network.
Director of Research	know how many papers were published in a given year	I can see how the School's research output varies over time.
Director of Research	know how many external co-authors an author has	I can understand his/her external impact factor.
Director of Research	search for an author	I can get statistics for individual members of staff.
Quality Assurance Tester	be able to run all the tests in one suite, rather than as separate test cases	I can more easily set up continuous integration and coverage monitoring.
Product Owner	have a "favourite icon" for the application	I can easily locate the application in my list of tabs or bookmarks.
Lead Engineer	rename the comp61542 code module	we can offer multiple versions of this application without namespace clashes.
Product Owner	be sure that all generated HTML pages validate correctly	we can show that this application is accessible.

## non-functional requirements
The HTML must be valid.
The application must be usable.
The application must be accessible.
All characters should be correctly displayed.