## Sheet1
As a/an… | I want to… | So that… | Developer | Time Estimate | Dev Time | Tester(s) | Time Estimate | Dev Time
Director of Research | search for an author | i can know the auther's information | Lynne Yingying Huang | 2 hrs | 1.5 hrs | Lynne Yingying Huang | 2 hrs | 1.3 hrs
Director of Research | Publish sole-author data to front-end | i can get the information i want | Mark kynigos Myriam Awaji | 3 hrs | 1.5 hrs | Mark kynigos Tian Yuan | 3 hrs | 2 hrs
Director of Research | how many sole-author papers each author has | I can get statistics for individual members of staff. | Mark kynigos Myriam Awaji | 3 hrs | 2.5 hrs | Mark kynigos Tian Yuan | 3 hrs | 2 hrs
Director of Research | type of publications, appearing times, co-authors each author has | i can get the information i want | Lynne Yingying Huang | 2 hrs | 1.5 hrs | Mark kynigos Tian Yuan | 2 hrs | 1.5 hrs